## Sheet1
Activities Table
Date | Who | [5 empty] | Type of Activty | Number of hours spent | Purpose | Output | Hours spent
| Rami | Youssef | Nicolas | Fouad | Akshey | Benoit |  |  |  |  | Rami | Youssef | Nicolas | Fouad | Akshey | Benoit
Sprint 1
2024-09-12 | x | x | x | x | x | x | In person lab meeting | 1 | Creating teams, choosing teammates for Peer Assessment project and deciding what programming languages and framework to use and what kind of database to use | "Future Coders" name is selected for the team, teammates were chosen and GitHub account is created. HTML, CSS, Javascript and Node.js were the languages to use, and CSV file was the primarly database | 1 | 1 | 1 | 1 | 1 | 1
2024-09-19 | x | x | x | x | x | x | In person lab meeting | 1.5 | Determine User stories, plan out the tasks for sprint one and discuss the division of work | The 3 user stories where determined and finalized. Tasks where determined and assinged to all group members, and React was the added framework to work on for this project and a csv database will be used that will store the users names and emails in plain text and their passwords will be hashed | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2024-09-19 | [5 empty] | x | Individual work (code editing) | 1 | Background research and Front end UI developement | Deepened understanding of React, HTML and Javascript. In addition, very basic UI for user team display was created | - | - | - | - | - | 1.5
2024-09-21 | x | x |  | x |  |  | Individual work (code editing + React.js tutorial learning) | 5.5 | Learning React.js in order to implement basic front end pages. Role selection page (student or teacher button), Log in and Sign up pages were needed to be implemented | Create login feature (Youssef), create role selection feature (Fouad) and create sign up feature (Rami) | 2.5 | 2 | - | 1 | - | -
2024-09-21 |  |  | x |  | x |  | Individual work (MongoDB tutorial learning) | 2 | Learning MongoDB to be used as a principle database instead of csv file | A good understanding of mongoDB databases and how to save information inside it | - | - | 2 | - | 2 | -
2024-09-25 |  |  | x |  | x |  | Individual work (code editing) | 1.5 | Implementing mongoDB to save information for both students and teachers | A basic MongoDB is obtained in order to save personal information of students and teachers (First Name, Last Name, email, password and role) | - | - | 1.5 | - | 1.5 | -
2024-09-26 | x | x | x | x | x | x | In person meeting at library + code editing | 3.5 | Try to fix the log in and sign up features issues. Fixing server issues and fixing the database (not approving log-ins) | Log in and Sign up bugs were fixed and improved. Node.js is used to fix the server issue. Also, deciding to make a mongoose database rather than use a csv file | 1.5 | 1.5 | 0.5 | 1 | 0.5 | 1
2024-09-26 | x | x | x | x | x | x | In person lab meeting | 1.5 | Discuss how to implement Mongoose instead of a CSV file, how the Team's creation could be improved for the teacher’s dashboard and how to make the teams visible for both teachers and students. | Teams will never be stored on the database, rather they will be displayed on the dashboards. Also, signup, login feature and the primary version of the team's creation are demonstrated to the TA. | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
2024-09-28 | x | x |  | x |  |  | Individual Activity (code editing) | 3.5 | Create teacher's and student's dashboard front end templates (teacher's dashboard contains "Create a new team" button) and work on "Create teams" front end page for teacher's role | A functional dashboard for the teacher with a create team feature and a blank dashboard for the students ( For now). Teams will neither be stored in the database, nor they will be shown on both dashboards. | 0.5 | 1 | - | 2 | - | -
30-Sept-2024 | [5 empty] | x | Individual Activity | 4 | Project Management and Documentation | Creation of Sprint plan, User stories, Tasks and Time tracking document | - | - | - | - | - | 4
30-Sept-2024 |  |  | x | x | x |  | Individual Activity (code editing) | 3 (0.5 for Fouad) | Implementing the team creation on teacher side and team viewing on student side. Also adding a go back button on team creation page | Teacher can now select students to be on teams and they will be viewed on his dashboard page. Students can now view in which team they are in and with who afterwards through their individual dashboard page. Teacher can also view all the students in the teams on the teacher dashboard. Role selection page is removed so the website is able to recognize user's role based on the data in MongoDB database during login procedure (Akshey and Nicolas). Also, Go back button to the home page was added in Teacher's creating teams page and a bug was fixed in creating teams form to prevent creating empty teams (Fouad) | - | - | 3 | 0.5 | 3 | -
[10 empty] | Total hours | 8.5 | 8.5 | 11 | 8.5 | 11 | 10.5