## Sheet1
Issue # | User Story Title/Task Title | Description/Associated Tasks | Story points | Priority | Risk | Assign | Sprint
#1 | #17 Teacher sign up page | -Create front end UI | 5 | HIGH | High, part of main functionality | Fouad, Youssef, Rami | 1
-Create back end function to store sign-up info into DB
-Create back end function to verify that user hasn't already signed up
-Create Teacher drop down option to UI in dashboard
#2 | #17 Student sign up page | -See Issue #1 | 5 | HIGH | High, part of main functionality | Fouad, Youssef, Rami | 1
-Make student team viewable for student in Dashboard
-Make sure that if email already exists, cannot sign up, only log in
#3, #4 | #17,18 Creation of Database | -Create MangoDB database to store user data | 4 | Medium, | Medium, not required as part of sprint Deliverables | Benoit, Akshay, Nicolas | 1
-Ensure students only are viewable for teachers when creating teams
-Add DB functionality to other tasks
#5 | #20 Teacher log on page | -Create front end UI | 5 | HIGH | High, part of main functionality | Fouad, Youssef, Rami | 1
-Create backend function to compare sign-in details to the DB
-Create Failed sign in redirect
-Create successful sign-in redirect
#6 | #20 Student log on page | See #5
#7 | #18 Create Teacher Team creator | -Create overall front end UI | 3 | HIGH | High, part of main functionality | Fouad, Youssef, Rami | 1
-Create table of students
-Create UI elements to allow assigning students to teams
-Create backend function to retrieve list of students from DB
-Create backend function to store the teams
#8 | #19 Create Student team viewer | -Create overall front end UI | 3 | HIGH | High, part of main functionality | Benoit, Fouad, Rami, Youssef | 1
-Create team display table
-Create backend function to retrieve team information
Note on B1: TO DO: Add DB stuff, Story points and Roles -Benoit Moreau